## Sheet1
Sl.No. | Phase | Activity | Priority | Integration Type | Ownership | Status | Assigned to | Documentation | Planned Effort (LH) | Actual Effort (LH) | Planned Start Date | Actual Start Date | Planned Finish Date | Actual Finish Date | Remarks 11-Dec-24 | Remarks 18-Dec-24 | Remarks 25-Dec-24 | Remarks 01-Jan-25 | Remarks 09-Jan-25 | Remarks 23-Jan-25 | Remarks 29-Jan-25 | Remarks 13-Feb-25 | Remarks 27-Feb-25 | Remarks 06-Mar-25 | Remarks 13-Mar-25 | Remarks 20-Mar-25 | Remarks 27-Mar-25 | Remarks 10-Apr-25
1 | E-Invoice Integration - Bi Directional |  | 1 | Extension | E-Inv Team | Completed | Varun Sai | Completed |  |  | 2024-04-29 | 2024-04-29 | 2024-06-30 | 2024-06-30 | Testing failed in Prevalidation , Technical team is fixing | Testing failed in Prevalidation , Technical team is fixing | Testing failed in Prevalidation , Technical team is fixing |  | Completed
9 | Supplier Update - Inbound |  |  | Integration | Asad | Completed | Asad | Completed | [17 empty] | Completed
19 | Attachment Download - Requisition - Outbound |  |  | Integration | Varun Sai 1 | Completed | Varun Sai | Completed | [16 empty] | Completed
20 | Attachment Upload - Requisition - Inbound |  |  | Integration | Damu | Completed | Varun Sai | Completed |  |  |  |  | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  |  |  |  | Completed |  |  | Completed
21 | Attachment Download - PO - Outbound |  |  | Integration | Varun Sai 2 | Completed | Varun Sai | Completed | [16 empty] | Completed
22 | Attachment Upload - PO - Inbound |  |  | Integration | Damu | Completed | Varun Sai | Completed |  |  |  |  | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  |  |  |  | Completed |  |  | Completed
23 | Attachment Download - Receipt - Outbound |  |  | Integration | Varun Sai 3 | Completed | Varun Sai | Completed | [16 empty] | Completed
24 | Attachment Upload - Receipt - Inbound |  |  | Integration | Varun Sai | Completed | Varun Sai | Completed |  |  | 2024-07-23 | 2024-07-23 | 2024-12-22 |  | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Development is completed , Documentation is pending | [7 empty] | Completed
25 | Attachment Download - AP Invoice - Outbound |  |  | Integration | Varun Sai 4 | Completed | Varun Sai | Completed | [16 empty] | Completed
26 | Attachment Upload - AP Invoice - Inbound |  |  | Integration | Damu | Completed | Varun Sai | Completed |  |  | 2024-06-24 | 2024-06-24 | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  |  |  |  | Completed |  |  | Completed
27 | Attachment Download - AP Payment - Outbound |  |  | Integration | Varun Sai 5 | Completed | Varun Sai | Completed | [16 empty] | Completed
28 | Attachment Upload - AP Payment-Inbound | Inbound |  | Integration | Varun Sai | Completed | Varun Sai | Completed |  |  | 2024-07-19 | 2024-07-19 | 2024-12-22 |  | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Development is completed , Documentation is pending | [7 empty] | Completed
29 | Attachment Download - AR Invoice - Outbound | Outbound |  | Integration | Varun Sai 6 | Completed | Varun Sai | Completed | [16 empty] | Completed
30 | Attachment Upload - AR Invoice - Inbound | Inbound |  | Integration | Damu | Completed | Varun Sai | Completed |  |  | 2024-06-24 | 2024-06-24 | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  |  |  |  | Completed |  |  | Completed
31 | Attachment Download - AR Receipt - Outbound | Outbound |  | Integration | Varun Sai 7 | Completed | Varun Sai | Completed | [16 empty] | Completed
32 | Attachment Download - Bank Statement - Outbound | Outbound |  | Integration | Varun Sai 8 | Completed | Varun Sai | Completed
43 | Receipt Creation - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-03-28 | 2024-03-28 | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  |  |  |  | Completed |  |  |  |  | Completed
46 | Attachment Upload -Supplier attachments - Inbound | Inbound | 2 | Integration | Damu | Completed | Varun Sai | Completed |  |  | 2024-03-03 | 2024-03-03 | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  |  |  |  | Completed
47 | Attachment Download -Supplier attachments - Outbound | Outbound |  | Integration | Varun Sai | Completed | Varun Sai | Completed | [16 empty] | Completed
48 | Receipt delete - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-06-10 | 2024-06-10 | 2024-06-18 | 2024-06-18 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Completed on 01-Jan-25
49 | Apply Receipt - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-04-18 | 2024-05-22 | 2024-06-04 | 2024-06-04 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Task completed
50 | Apply on account Receipt - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-05-12 | 2024-05-12 | 2024-05-20 | 2024-05-20 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  | Completed
51 | Unapply AR receipt - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-05-29 | 2024-05-29 | 2024-06-06 | 2024-06-06 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Completed on 01-Jan-25
52 | Reverse Receipt - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-04-03 | 2024-04-03 | 2024-04-21 | 2024-04-21 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Completed on 01-Jan-25
53 | Void Payment - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-04-24 | 2024-04-24 | 2024-04-29 | 2024-04-29 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending |  |  |  |  | Completed
54 | Create and apply AP payments - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-08-22 | 2024-08-22 | 2024-08-05 | 2024-08-05 | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Development is completed , Documentation is pending |  | Completed
55 | AR Ajustments - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-07-30 | 2024-07-30 | 2024-08-11 | 2024-08-11 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Task completed
56 | Acvitiy apply AR receipts - Inbound | inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-06-10 | 2024-06-10 | 2024-06-24 | 2024-06-24 | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Completed on 01-Jan-25
57 | Create Misc Receipts - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-05-12 | 2024-05-12 | 2024-05-15 | 2024-05-15 | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Task completed
58 | Create AP invoice Apply - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-08-26 | 2024-08-26 | 2024-09-09 | 2024-09-09 | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Task completed
59 | Create AP Invoice Unapply - Inbound | Inbound |  | Integration | Varun | Completed | Varun Sai | Completed |  |  | 2024-08-26 | 2024-08-26 | 2024-09-09 | 2024-09-09 | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Task completed
63 | Attachment Upload - Requisition Lines - Inbound | Inbound |  | Integration | Damu | Completed | Varun Sai | Completed |  |  | 2024-02-19 | 2024-02-19 | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending
64 | Attachment Upload - PO Lines - Inbound | Inbound |  | Integration | Damu | Completed | Varun Sai | Completed |  |  | 2024-03-12 | 2024-03-12 | 2024-12-22 |  | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending | Development and Documentation are completed , Archiving of Configurations is pending
2 | COA Value - Inbound |  |  | Integration | Md Abdul Rehman | Completed | Md Abdul Rehman | Completed | [14 empty] | Completed
3 | COA Value - Outbound | Outbound |  | Integration | Md Abdul Rehman | Completed | Md Abdul Rehman | Completed | [15 empty] | Completed
6 | GL Period Status - Outbound |  |  | Integration | Rahul Vardhan | Completed | Rahul Vardhan | Completed
7 | Supplier Creation - Inbound |  |  | Integration | Hussian Jamel | Completed | Hussian Jamel | Completed | [15 empty] | Completed
8 | Supplier Creation - Outbound |  |  | Integration | Rahul Vardhan | Completed | Rahul Vardhan | Completed | [18 empty] | Completed
11 | Customer Creation - Inbound |  |  | Integration | Rahul Vardhan | Completed | Rahul Vardhan | Completed | [16 empty] | Completed
12 | Customer Creation - Outbound |  |  | Integration | Rahul Vardhan | Completed | Rahul Vardhan | Completed | [16 empty] | Completed
13 | Customer Update - Inbound |  |  | Integration | Rahul Vardhan | Completed | Rahul Vardhan | Completed | [16 empty] | Completed
16 | Supplier Invoice - Outbond |  |  | Integration | Rahul Vardhan | Completed | Rahul Vardhan | Completed | [19 empty] | Completed
17 | Customer Invoice - Inbound |  |  | Integration | Md Abdul Rehman | Completed | Md Abdul Rehman | Completed
18 | Customer Invoice - Outbound |  |  | Integration | Md Abdul Rehman | Completed | Md Abdul Rehman | Completed | [19 empty] | Completed
34 | Attachment Download - GL Journal - Outbound |  |  | Integration | Varun Sai | Completed | Varun Sai | Completed
37 | Requisition Creation - Inbound | Inbound |  | Integration | Asad | Completed | Asad | Completed | [15 empty] | Completed
38 | Requisition Creation - Outbound | Outbound |  | Integration | Md Abdul Rehman | Completed | Md Abdul Rehman | Completed | [18 empty] | Completed
39 | PO Creation - Inbound | Inbound |  | Integration | Md Abdul Rehman | Completed | Md Abdul Rehman | Completed | [15 empty] | Completed
40 | PO Creation - Outbound | Outbound |  | Integration | Md Abdul Rehman | Completed | Md Abdul Rehman | Completed
66 | Property Management Extension to Oracle Fusion | Inbound |  | Extension | Rambabu | Completed | Md Abdul Rehman | Completed | 32 |  | 2024-12-05 | 2024-12-05 | 2024-12-10 |  | FSD documents Review changes updates is in progress | FSD document Review is in progress | Development is in progress
5 | Journals - Outbound |  |  | Integration | Asad | Completed | Asad | Completed | [17 empty] | Completed
15 | Supplier Invoice - Inbound |  |  | Integration | Ajmal | Completed | Ajmal | Completed | [12 empty] | Completed
60 | AR credit memo Application - Inbound | inbound |  | Integration | Ajmal | Completed | Ajmal | Completed |  |  | 2024-08-26 | 2024-08-26 | 2024-09-09 | 2024-09-09 | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Development is completed , Documentation is pending |  |  |  | Completed
62 | Update AR invoice - Inbound | Inbound |  | Integration | Ajmal | Completed | Ajmal | Completed |  |  | 2024-04-02 | 2024-04-02 | 2024-04-04 | 2024-04-04 | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Development is completed , Documentation is pending |  |  | Completed
4 | Journals -Inbound |  |  | Integration | Hussian Jamel | Completed | Hussian Jamel | Completed | [14 empty] | Completed
69 | Chatbot Integration HCM |  |  | Extension | Ajmal | Completed | Ajmal | Completed
72 | Custom AP Invoice Page with minimum fields which would integrate to standard AP Invoice |  |  | Extension | T Divya | Completed | Hussian Jamel
73 | Custom AR Invoice Page with minimum fields which would integrate to standard AR Invoice |  |  | Extension | T Divya | Completed | Hussian Jamel | Completed
61 | Fleet Management - Bidirectional | Inbound |  | Integration | Ajmal | Completed | Ajmal | Completed |  |  | 2024-09-09 | 2024-04-16 | 2024-09-14 | 2024-09-14 | Development is completed , Documentation is pending | Development is completed , Documentation is pending | Development is completed , Documentation is pending |  |  | Completed
10 | Supplier Update - Outbound |  |  | Integration |  | Dropped | [19 empty] | Completed
14 | Customer Update - Outbound |  |  | Integration | Rahul Vardhan | Dropped | [18 empty] | Completed
33 | Attachment Upload - Bank Statement- Inbound | Inbound |  | Integration | Varun Sai | Planned
35 | Attachment Upload - GL Journal - Inbound |  |  | Integration | Varun Sai | Planned
36 | Real Estate Solution - Inbound |  | 3 | Extension |  | Planned
41 | Requisition Approval Submission - Inbound | Inbound |  | Integration | Md Abdul Rehman | WIP | Md Abdul Rehman
42 | PO Approval Submission - Inbound | Inbound |  | Integration | Md Abdul Rehman | WIP | Md Abdul Rehman
44 | Supplier Payment Integration with Bank - Outbound | Outbound |  | Extension |  | Planned
45 | Fleet Management - Bidirectional | Bi Directional | 2 | Extension | Ajmal | Completed | Ajmal |  |  |  | 2024-12-08 | 2024-12-08 |  |  | Working is in progress | Working is in progress | Working is in progress | [8 empty] | Completed
65 | Time Entry Extension to Oracle Fusion OTL | Inbound |  | Extension | Sowmya | Completed | Hussian Jamel |  | 40 |  | 2024-12-02 | 2024-12-03 | 2024-12-10 |  | FSD documents Review changes updates is in progress | FSD documents Review changes updates is in progress | Development is in progress
67 | Project Management with Subcontracting module |  |  | Integration | Syed Jeelani | Planned
68 | LG (Letter of Guarantee) / LC (Letter of Credit) |  |  | Extension | Varun Sai | Planned | Varun Sai
70 | Project Costing Integration With Payroll ( Business trips, Conferences ,etc) |  |  | Integration |  | Planned
71 | Auto Create LCM Charges and ASN (Advance shipment Notice) while entering the PO information. |  |  | Extension | Syed Jeelani | Planned